## Risks
Risk ID | Description | Impact | Likelihood | Mitigation | Owner | Status
R001 | Ollama requires too much RAM for smooth operation | High | Medium | Test on 16GB machine, optimize model selection | Alan | Open
R002 | SQLite performance degrades with large datasets | med | Low | Monitor query times, add indexes if needed | Alan | OPEN
R-003 | Tauri build complexity might slow development | Medium | high | Learn Rust basics, keep frontend simple |  | Monitoring
R002 | Database might not scale well | Medium | Low | Use WAL mode, consider migration path | Alan | mitigated
R004 | LLM extraction quality inconsistent across doc types | HIGH | High | Improve prompts, test with real examples | alan | Open
R005 | No budget for commercial LLM APIs if Ollama fails | Critical | Low | This is the whole point of the project, stick to local | Alan | Accepted
R006 | User (me) might abandon project if too complex | High | Medium | Keep scope tight, ship working features incrementally | Alan | open

## Actions & Issues
ID | Action/Issue | Owner | Due Date | Status | Priority
A001 | Complete database schema design | Alan | 2026-02-20 | Done | High
A002 | Implement batch upload endpoint | Alan | 2025603-05 | In Progress | HIGH
A003 | Test Ollama models (mistral-nemo, llama3.1, deepseek-r1) | Alan | 2026-02-25 | Done | Med
A004 | Build Settings page with document types CRUD | Alan | 2026-03-10 | Not Started | Medium
A005 | Add intake folder scanning feature | TBD | ASAP | Blocked | High
A006 | Write integration tests for batch upload | Alan | 2026-03-12 | In Progress | Low
| Fix drag and drop in UploadPanel (onDragEnter missing) | Alan | 2026-03-08 | DONE | Critical
A008 | Optimize LLM prompts for better extraction | Alan |  | Open | High
A004 | Document API endpoints in Swagger | Alan | 2026-03-15 | Not Started | Low

## Dependencies
Task A | Relationship | Task B | Notes
Database schema complete | blocks | Backend API development | Can't build endpoints without schema
Batch upload endpoint | BLOCKS | Frontend upload UI | Frontend needs working endpoint to test
Ollama integration working | enables | LLM extraction features
Settings page | relates to | Document types management | Same feature different wording
Backend API stable | blocks | Tauri frontend development | Need API to integrate with
llm_service.py complete | blocks | Chat interface | Chat needs LLM service methods

## NOTES_DO_NOT_DELETE
These are just random thoughts
TODO: Add scope_items table
RISK: What if someone uploads 1000 PDFs at once?
Action: Research APScheduler for daily briefings - Alan - March 18
Deadline: V2 prototype demo March 28 2026
Budget note: Ollama is free but electricity costs are real lol
IMPORTANT: Never add external API calls breaks GDPR compliance