## Risk Register
Project Intel V2 - Risk Register
Last Updated: Feb 29 2026 (needs updating)
Risk ID | Category | Description | Impact | Likelihood | Severity | Mitigation Strategy | Owner | Status | Last Reviewed
R-TECH-001 | Technical | Ollama memory usage exceeds available RAM | High | Medium | 8/10 | Test on 16GB machine, use smaller models | Alan | Open | 2026-02-25
R-TECH-002 | Technical | SQLite write performance degrades with concurrent uploads | Medium | Low | 4 | Use WAL mode, batch inserts | Alan | Mitigated | 2026-02-26
R-SCOPE-001 | Scope | Feature creep from V1 wishlist items | HIGH | HIGH | Critical | Strict scope control, defer to V3 | Alan | Monitoring | 2026-03-05
R-TECH-003 | Technical | LLM extraction misses actions in complex documents | High | High | 9/10 | Improve prompts, add examples, test edge cases | Alan | Open | 2026-02-28
R-DEV-001 | Development | Solo developer = single point of failure | Critical | Medium | 10 | Document everything, keep code clean | Alan | Accepted | 2026-02-20
R-TECH-004 | Technical | Tauri CSP might block needed functionality | med | Low | 3/10 | Test CSP rules, adjust as needed | Alan | Closed | 2026-02-24
R-UX-001 | User Experience | Drag-and-drop might confuse user (me) | Low | Low | 2 | Add clear visual feedback | Alan | Resolved | 2026-03-07
R-DATA-001 | Data | No backup strategy for SQLite database | CRITICAL | High | 12/10 | Implement automated backups, test restore | TBD | URGENT | 2026-05-04
R-TECH-005 | Technical | Model selection logic too complex | Medium | Medium | 5/10 | Simplify to document-type level selection | Alan | In Progress | 2026-04-06
R-COST-001 | Budget | Development time exceeding estimate | Med | Very High | 7 | Focus on MVP features only | Alan | open | 2026-03-03
NOTES:
- Severity scoring is inconsistent (some numeric, some text, some x/10)
- Need to review R-DATA-001 ASAP, no backup is bad
- Some statuses haven't been updated in over a week
ACTION ITEM: Standardize severity scoring - Alan - March 10
ACTION: Review all 'Open' risks weekly - Alan - ongoing