# PROJECT INTEL V2 - REVISED PROJECT PLAN

Version 2.1 (Supersedes v1.3 and v2.0)

Date: March 6, 2026

Status: ACTIVE

# EXECUTIVE SUMMARY

Original plan was too optimistic. After 3 weeks of development we are adjusting timelines and scope. Core functionality remains unchanged but adding buffer for complexity discovered during implementation.

# REVISED TIMELINE

Phase 1: Backend Development (Feb 12 - Feb 28) ✓ COMPLETE

- Database schema design and implementation

- FastAPI endpoints for CRUD operations

- Ollama integration and model testing

- Document processing pipeline

Phase 2: Frontend Foundation (Feb 26 - March 15) ← IN PROGRESS

- Tauri setup and configuration

- Settings page (COMPLETE)

- Batch upload UI (IN PROGRESS - Prompt 4)

- Data tables with pagination

- Chat interface

Phase 3: Integration & Polish (March 16 - March 30)

- End-to-end testing

- Notification system implementation

- Performance optimization

- Bug fixes and UX improvements

Phase 4: Launch Prep (March 31 - April 20) ← EXTENDED

- Documentation writing

- Demo video creation

- Final testing

- V2.0 release

# KEY MILESTONES

✓ Feb 20: Database schema finalized (WAS: Feb 18)

✓ Feb 28: Sprint 1 complete (ON TIME)

• March 12: Frontend Prompts 4-6 complete (WAS: March 10)

• March 22: Working prototype demo (WAS: March 28 - MOVED UP???)

• April 5: All features complete (NEW)

• April 20: V2.0 Release (WAS: April 15)

# SCOPE CHANGES

IN SCOPE (confirmed):

- Batch document upload with type selection

- Intake folder monitoring

- Structured extraction to database

- Q&A chat interface

- Daily briefing notifications

- CRUD for all data types

DEFERRED TO V3:

- Excel multi-sheet processing

- Automated file system watching

- Dependency visualization graphs

- Sounding board mode

- Prompt version control

- External integrations (Slack, Google Drive)

# CRITICAL SUCCESS FACTORS

1. Maintain build momentum - complete 6-prompt sequence without distraction

2. Defer optimization and polish until core features stable

3. Test with realistic messy documents (like these ones)

4. Keep scope tight - resist feature creep

# RISKS & MITIGATION

See Risk Register for full details. Top 3:

R-DATA-001: No backup strategy (URGENT - implementing this week)

R-SCOPE-001: Feature creep from wishlist (ACTIVE - strict control)

R-DEV-001: Single developer SPOF (ACCEPTED - good documentation)

# DEPENDENCIES

External:

- Ollama service running and accessible

- Required models downloaded (mistral-nemo, llama3.1, deepseek-r1)

Internal:

- Backend API stability (DONE)

- Frontend component library choices (DONE)

# NOTES

• Prototype demo date conflict: Week 3 notes say March 28, this doc says March 22

• Need to reconcile with kickoff doc which said "end of March"

• April 15 vs April 20 release - which is it?

• ACTION: Align all project documents to consistent timeline - Alan - March 9