## Q1 Actions Review
Project Intel V2 - Q1 Actions Review
Period: Feb 12 - March 31, 2025
Action ID | Description | Owner | Due Date | Status | Completion Date
A-Q1-001 | Setup project structure and Git repo | Alan | 2026-02-15 | COMPLETED | 2026-02-15
A-Q1-002 | Design and implement database schema | Alan | 2026-02-20 | DONE | 2026-03-21
A-Q1-003 | Integrate Ollama SDK | Alan | 2026-02-25 | Finished | 2026-03-26
A-Q1-004 | Build batch upload endpoint | Alan | 2026-03-05 | CLOSED - Delivered | 2026-04-06
A-Q1-005 | Create Settings page UI | Alan | 2026-03-06 | Complete | 2026-02-08
A-Q1-006 | Implement intake folder scanning | Alan | 2026-03-12 | IN PROGRESS
A-Q1-007 | Build chat interface | Alan | 2026-04-01 | Not Started
A-Q1-008 | Add notification system | Alan | 2026-04-02 | Open
A-Q1-009 | Write integration tests | Alan | 2026-04-03 | CANCELLED - Out of scope for V2 | N/A
A-Q1-010 | Performance optimization | Alan | 2026-04-06 | DEFERRED to V2.1

## Q1 Risks Review
Risk Status Summary
Risk ID | Description | Impact | Status | Resolution Date | Notes
R-001 | Ollama memory issues | High | RESOLVED | 2025-03-11 | Hardware upgrade fixed it
R-002 | SQLite performance concerns | Medium | MITIGATED | 2025-02-26 | WAL mode implemented
R-003 | Tauri learning curve | Medium | CLOSED - No longer relevant | 2025-03-01 | Team ramped up quickly
R-004 | LLM extraction quality | High | ACTIVE - Monitoring |  | Improved but still tuning
R-005 | No budget for cloud APIs | Critical | ACCEPTED |  | This is design constraint
R-006 | Single developer SPOF | High | Open |  | Ongoing risk
R-007 | Scope creep from wishlist | High | MONITORING |  | Strict control in place

## Q1 Deadlines
Milestone Tracking
Milestone | Target Date | Status | Actual Date
Database schema finalized | 2025-02-20 | MET | 2025-02-19
Sprint 1 complete | 2025-02-28 | ACHIEVED | 2025-02-28
Backend API stable | 2025-03-01 | DELIVERED | 2025-03-01
Settings page complete | 2025-03-10 | DONE | 2025-03-08
Prompts 1-3 finished | 2025-03-10 | COMPLETED EARLY | 2025-03-09
Prompts 4-6 finished | 2025-03-15 | MISSED - Extended to 3/18
Prototype demo | 2025-03-28 | UPCOMING
V2.0 Release | 2025-04-20 | PENDING