# Project Kickoff Meeting — 5 April 2026

# Attendees

Alan R (PM), Sarah K (Dev Lead), Mike T (Finance), Lisa P (QA)

# Action Items

Alan to finalise vendor contract by April 12 (HIGH priority)

Sarah to set up CI/CD pipeline by April 20 (HIGH priority)

Mike to approve Q2 budget allocation by April 10

Lisa to write test plan for phase 1 by April 18 (MEDIUM priority)

# Deadlines

Phase 1 development complete: May 1 2026

User acceptance testing: May 15 2026

Go-live: June 1 2026

# Risks Identified

Resource availability risk: Dev team split across two projects until April 30. Medium impact, medium likelihood. Mitigation: prioritise this project for the first two weeks.

Scope creep risk: Stakeholders requesting additional reporting features not in original plan. High impact, high likelihood. Mitigation: strict change control process.

# Dependencies

Budget approval enables vendor contract signing.

Vendor contract blocks project kickoff.