## RAID Log
Type | Description | Owner | Impact | Status
Risk | Vendor delivery delayed by 2+ weeks due to supply chain issues | Alan R | High | Open
Risk | Budget approval may slip past April 15 deadline | Finance | Medium | Open
Action | Review and sign vendor proposal | Alan R | High | Open
Action | Schedule kickoff meeting with stakeholders | PM | Medium | Open
Issue | Legacy API endpoint returning 504 errors intermittently | Dev Lead | High | In Progress
Dependency | Budget sign-off must happen before vendor contract | Finance | High | Blocking